## Put the above plan in visual pr
Phase / Milestone | Duration (Weeks) | Start Date | End Date | Key Deliverables / Focus
Sprint 0: Foundation & Setup | 2 | [Start] | [+2W] | Core Dev Environment, Basic Infrastructure (Local Docker, Initial CI/CD), LiteLLM Setup, Initial K8s Exploration, Secrets Management.
Phase 1: Basic Backend & UI | 2 | [+2W] | [+4W] | Basic FastAPI Backend (direct LLM), Minimal React UI, Basic MongoDB Integration.
Phase 2: LangGraph & First Tool | 3 | [+4W] | [+7W] | LangGraph Integration (initial flow), Stock Information Tool, Basic Short-Term Memory.
Phase 3: Second Tool & Routing | 2 | [+7W] | [+9W] | Weather Data Tool, Enhanced LangGraph Routing (Intent Classification).
Phase 4: Vector DB Search Tool | 3 | [+9W] | [+12W] | Set up Vector DB, Implement RAG Search Tool, Integrate into LangGraph Routing.
Phase 5: Basic RAG Integration | 2 | [+12W] | [+14W] | LangGraph Node for Integrating RAG Results into Context.
Milestone 1: Core Agent Functional |  |  | [+14W] | Core agent with basic RAG and multiple tools (Stock, Weather, Search) is functional.
Phase 6: Advanced Agent Logic | 4 | [+14W] | [+18W] | Comprehensive LangGraph for Multi-Step Reasoning and Tool Orchestration.
Phase 7: Response Refinement | 2 | [+18W] | [+20W] | Implement and Integrate the 'Final Response Refiner' Tool/Node.
Phase 8: Full UI & History | 4 | [+20W] | [+24W] | Feature-Rich React UI (LLM Select, History Management, Preferences), Backend APIs for UI.
Milestone 2: Full UI Integrated |  |  | [+24W] | User interface with core agent capabilities and history management is complete.
Phase 9: Deep Memory Integration | 4 | [+24W] | [+28W] | Implement Episodic and Long-Term Memory (Vector DB, MongoDB), Develop Background LTM Updater (LangGraph Subgraph).
Phase 10: Observability & Advanced RAG | 4 | [+28W] | [+32W] | Integrate OpenTelemetry (Tracing, Metrics, Logging), Implement Advanced LightRAG Features (Dynamic Modes, Graph Search), Document Ingestion Pipeline.
Milestone 3: Feature Complete |  |  | [+32W] | All core features, memory systems, advanced RAG, and observability are implemented. Ready for rigorous testing.
Testing & QA | 4 | [+32W] | [+36W] | Comprehensive Unit, Integration, and End-to-End Testing. Performance and Security Testing.
Deployment & Go-Live Prep | 2 | [+36W] | [+38W] | Staging Environment Setup, Final Testing, User Acceptance Testing (UAT), Production Deployment Preparation.
Go-Live | 1 | [+38W] | [+39W] | Production Deployment.
Post-Launch Monitoring & Iteration | Ongoing | [+39W] | ... | Monitoring system health, addressing bugs, gathering user feedback for future improvements.